## Sheet1
Task	Original estimation (in hours)	Actually took (in hours)
#1: Get rid of old IE events	2
#8: Minimap - uninitialized	3
#12: Health page	3
#15: Able to duplicate a figure Ctrl-D	4
#20: Diagramo "host" format + crons
#21: Link on figure	4
#22: Rounded connectors	4
#23: Grid dotted instead of lines
#26: Shift + Select = select many	4
#28: Fill, outline, font, etc will have special icons	3
#30: Highlight "about to connect" connection points	4
#32: Dotted, dashed line support	4
#34: Connector end in a filled arrow by default	1
#38: Organic connectors	4
#48: Web installer
#53: No image for network element
#58: Copy style - format paintbrush
#59: After undo on moving group: TypeError: Cannot call method 'transform' of null	2
#60: After undo: TypeError: Cannot read property 'primitives' of null	2
#66: Snap to grid - not unchecked
#69: Hoover efect on icons	2
#70: beginPath() missing in many paint() methods	1

Total	47